WELL CIRCLE -- DEV TEAM TIMELINE 1-Week Sprint: Mon Jul 13 - Sun Jul 19, 2026

Scope for this sprint: the four priority workstreams from our dev-team meeting, plus sending the polished MVP video. The in-person meeting with Kuriftu is not being held this week -- we're only proposing dates for after Mahilet's Kenya trip.

| DAY | OWNER | DELIVERABLE | APPROACH |
| --- | --- | --- | --- |
| MON Jul 13 | Bezi | Full audit of Kuriftu's live services + current booking steps. | Go through the website end-to-end; list every service, category, and the exact steps a guest takes to book today. |
|  | Yoni | Technical scoping note for the Sheets integration. | Decide auth method, which fields sync (booking id, guest, service, date/time, status), and where in the confirmation step it hooks in. |
|  | Biniyam | One-page sketch of the pre-sale promo + re-entry triggers. | Review existing promotion/notification hooks already in the app; sketch who creates a promo and what nudges bring users back. |
|  | Anteneh | Annotated user-flow map + analytics tool decision. | Walk the full Home -> Explore -> booking -> confirmation path as a real user; flag friction points; pick the tracking approach. |
| TUE Jul 14 | Bezi | Structured service list ready for seeding. | Turn Monday's audit into a clean spreadsheet/JSON (name, category, description, price) formatted for engineering handoff. |
|  | Yoni | Working proof-of-concept: a test booking writes to a live Sheet. | Build the Sheets API connection (service account + write access) and confirm one test row lands correctly. |
|  | Biniyam | Backend endpoint + basic UI stub for creating a promotion. | Extend the existing promotions data model with the simplest version first -- a flat % discount tied to early sign-up. |
|  | Anteneh | First 2-3 analytics events live in test. | Instrument app-open, explore-view, and booking-start events using Monday's chosen tool. |
| WED Jul 15 | Bezi | Gap list comparing Kuriftu's steps to the app's booking flow. | Hand off the seeded service list to Yoni; flag any step Kuriftu has that the app doesn't yet (e.g. add-ons, room selection). |
|  | Yoni | Sheets sync wired into the real confirmation step. | Move the write-path from test to the actual booking confirmation trigger so every booking auto-logs. |
|  | Biniyam | Pre-sale promo live in test + first re-entry nudge draft. | Trigger the promo automatically for first-time visitors; draft a reminder nudge for users who haven't returned in X days. |
|  | Anteneh | Top 2 friction points fixed in a test build. | Simplify or clarify the worst friction points flagged on Monday. |
| THU Jul 16 | Bezi | Sign-off note on Explore content accuracy. | QA the seeded content against the live Kuriftu site -- nothing missing, pricing/descriptions correct. |
|  | Yoni | Status-update logic tested (cancellations, reschedules, conflicts). | Make sure the Sheet reflects changes after creation, not just the initial booking. |
|  | Biniyam | End-to-end presale + re-entry loop working in test. | Connect the nudge to the promo (e.g. "come back and use your discount before it expires"). |
|  | Anteneh | Video script/storyboard draft. | Script the MVP walkthrough -- what to show, in what order, what story it tells about the pilot. |
| FRI Jul 17 | Bezi | Explore section considered feature-complete for this sprint. | Support Anteneh with any content details needed for the video; close out remaining polish. |
|  | Yoni | Booking-to-Sheet flow confirmed stable end-to-end. | Full team test run acting as guests; fix anything that breaks. |
|  | Biniyam | Confirmed analytics events firing on promo view/redemption/re-entry. | Verify Anteneh's tracking actually captures the presale + re-entry loop, since that's what proves the feature works. |
|  | Anteneh | Raw video footage captured. | Record the MVP walkthrough following Thursday's script. |
| SAT Jul 18 | Anteneh | Polished MVP video, ready to send. | Edit the footage -- trim, captions/branding, voiceover if needed. |
|  | Yoni | Bug-free build + short internal integration note. | Final bug pass from Friday's test run; write a short note on how the Sheets integration works for the rest of the team. |
|  | Bezi + Biniyam | Punch-list of any remaining rough edges. | Walk the whole app as a first-time Kuriftu user would -- Explore, promo, booking, confirmation -- and log anything unresolved. |
|  | Whole team | 2-3 proposed meeting times sent to Mahilet. | Not holding the in-person meeting this week -- just proposing dates for after her Kenya trip. |
| SUN Jul 19 | Whole team | Punch-list items resolved. | Close out anything flagged Saturday. |
|  | Anteneh | Polished MVP video sent to Kuriftu. | Send the final video to Mahilet with a short note. |
|  | Whole team | Meeting slot confirmed once Mahilet responds. | Lock the date once she replies; leave pending otherwise. |
|  | Whole team | End-of-week check against success criteria. | Confirm this week's work plausibly moves new customers, repeat rate, and services-used once the pilot is live. |

SUCCESS CRITERIA TO KEEP IN VIEW

•  Increase new customers to wellness

•  Increase repeat rate

•  Increase the number of services used

Every deliverable above should trace back to at least one of these -- the Sheets integration and service audit support new-customer conversion, the presale/re-entry work supports repeat rate, and the Explore content + UX refinement support services used.

Well Circle -- Anteneh, Beza, Biniyam, Yonathan  |  Telegram Mini App . Ethiopia